## TasksList
Topic | Details of the task | Time needed in hours | Task owner | Start date | End date (Last week is not counted as we will need it for improvements) | Total Number of days | Rough estimate of how many hours to put every day
Front End
HTML landing page | This should be first page from where the user should be able to either sign-in or signup | 12
Sign-up Page | first time page where the user will enter his details and creates an account | 12
First page of the app + Meal Entry Page | This will be the first page where the user will be able to see all the options like Meal entry, visualization etc. By default the Meal Entry can be displayed. | 12
Vizualisation page | On this page user will be able to select various vizulizations from Calories, Macronutrients, Micro nutrients and select from period 1 day, 7 days or 1 month So total 3 x 3 = 9 vizualization pages. | 40
Database
Creation of user database | This should also provide examples of how to query this database. It will be helpful for the backend developer to use the query directly instead of thinking of how to write a query. Will save efforts | 16
Creation of USDA database | This should also provide examples of how to query this database. It will be helpful for the backend developer to use the query directly instead of thinking of how to write a query. Will save efforts | 16
Backend
backend for the User personal details page and account creation. This should include adding the details in the database. If user forgot his password then retriving the password and asking him to create a new one. |  | 24
backend for the meal entry details page. This should include adding the details in the database. Are we going to provide him the option to edit the details once he has saved it in the database?? |  | 16
Backend to calculate the nutrient amount and storing in userdatabase. Backend to query the USDA database and retrive the information about nutrients, calculation of nutrients for each meal_item and saving it in the food database of the user. |  | 20
Vizualization backend. Based on what vizualization period is selected and which nutrient to be vizualized, query the user database and retrive the desired information, do calculations and send the data to the visualization |  | 20
Flash app development and adding all the routes to it and checking of all is fine. |  | 24
Deployment of the flask app on heroku |  | 8
Buffer for unknown tasks. |  | 40
Total development |  | 260
Testing |  | 24
Bug fixing |  | 24
Proposal preparation |  | 6
Presentations preparation |  | 8
Total time (development + testing+ presentation) |  | 322
Per head time |  | 64.4 |  | 2020-03-10 | 2020-03-28 | 18 | 3.5778